## Progress bills
Progress bill template: advance, retention and UAE VAT 5%
Fill the white boxes. Everything else works itself out. One method for every bill, never mixed.
Contract value (before VAT, AED) |  | 1000000
Advance (% of contract) |  | 30
Retention (% of each bill) |  | 10
Deductions (Before VAT / After VAT) |  | Before VAT | Choose from the list
VAT rate (%) |  | 5
The advance tax invoice | Advance (before VAT) | VAT | Total
Raised when the advance is received (a tax point) | 300000 | 15000 | 315000
Bill | Work done to date (%) | Work this bill | Advance taken back | Retention held | Taxable amount | VAT on this bill | Payable | Billed to date (%) | Retention held to date | Check
1 | 30 | 300000 | 90000 | 30000 | 180000 | 9000 | 189000 | 30 | 30000 | OK
2 | 70 | 400000 | 120000 | 40000 | 240000 | 12000 | 252000 | 70 | 70000 | OK
3 | 100 | 300000 | 90000 | 30000 | 180000 | 9000 | 189000 | 100 | 100000 | OK
4
5
6
7
8
9
10
Total |  | 1000000 | 300000 | 100000 | 600000 | 30000 | 630000
Retention release (when you release it)
Retention to release |  | 100000
VAT on the release |  | 5000 | Held without VAT, so charged now
Total received on release |  | 105000
VAT declared on the whole contract |  | 50000 | Should be 5% of the contract once it is fully billed
Doing this every month? Mizarah does every progress bill for you: the advance, the retention and VAT declared once, on tax invoices in Arabic and English. 14 days free, no card: mizarah.com
Practical guidance, not tax advice. Percentage deductions only; penalties, discounts and variations are handled in the app.